## 1 GIA
Gender impact assessments
Table 1 - Gender impact assessments progress
Required | Required | Required | Required | Required | Required | Recommended | Recommended
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Employee Health and Wellbeing Policy | Policy | The Policy is designed for all MDHS employees and staff, and fosters the health and wellbeing of the MDHS Team | For Review | Yes | - All of staff survey implemented and responded to in 2023 by the WISH Team. - The feedback from the survey was used to expand on the initiatives put in place in 2022-23. - Feedback on implemented initiatives is gathered and reviewed in order to make improvements. - The WISH Team meets monthly. | Yes | We felt that females may be less likely to be able to access programs outside of ours given the the race and religion of some of our team. Therefore, we felt it was importatnt that staff could access programs during work hours, where outside of work factos can be put aside.
Smoke Free Policy | Policy | The Smoke Free Policy aims to proactively address smoking as a significant health risk for smokers and non-smokers, and thereby show public health leadership in relation to the issue of smoking. | For Review | No action taken | - Given legislation is directing how MDHS are to respond, there is little room for movement. - We have however considered the impacts of the directives, and provided purpose built areas for those who chose to smoke, provide free access to programs aimed at helping smokers stop smoking. - Education programs are in place, the smoke free policy is activley discussed at all induction sessions. | Yes | Based on research, males from certain cultural backgrounds are more likely to be impacted by this policy.
Attitude of Gratitude Recognition Policy | Policy | The policy outlines key principles to guide development and implementation of MDHS staff reward and recognition to improve staff morale and retention. | For Review | Yes | Education, support and training for the leadership team to ensure staff recognition is sincere, meaningful and inclusive of all genders. | Yes | The policy was reviewed in the context of its impact on various diverse groups and we did not identify intersectional factors which would impact on an employee being recognised or thanked for their work.
Continue to engage and educate leaders at MDHS to make staff recognition and gratitude part of everyday work culture.
Listen to staff feedback and adjust policy as needed.
Bereavement Policy | Policy | Policy to provide a consistent and caring response to MDHS team members experiencing bereavement and grief. | For Review | Yes | Support and training for the leadership team to ensure a caring response is provided to anyone needing support in a time of bereavement. | Yes | The policy includes specific mention of culturally sensitive support to be provided, for example by one of MDHS' Aboriginal Hospital Liaison Officers.
[5 empty] | Listen to staff feedback and adjust policy as needed. |  | There is also specific mention of support being provided which is appropriate for people with diverse religious beliefs
Child Safe Standards Policy | Policy | The policy outlines MDHS’ commitment to being a Child Safe organisation and to uphold the updated Child Safe Standards, developed to keep children and young people safe. | For Review | No action taken | This policy is directly informed by current Child Safe Standards and so the requirements are set. However, the Standards give particular mention to gender diversity in young people protected by the policy to ensure equity is upheld. | Yes | The standards in the policy include specific support for Aboriginal children and children from other culturally diverse backgrounds. Cultural safety is a high priority as a means to ensuring child safety and is a constant theme throughout the policy.
Consumer Feedback and Complaints Policy | Policy | The policy details the process for management of complaints in a fair, equitable and transparent manner, acted upon promptly and treated confidentially. | For Review | Yes | Gender identity can impact how or if a complaint is made, but there is no data on the gender impact during the complaint process. | Yes | The policy was reviewed in the context of its impact on various diverse groups and we did not identify intersectional factors which would impact a complaint process.
Recommend a review to establish if gender is a barrier to a complaint being made, or if it is a factor in the handling process.
Professional Presentation Policy | Policy | This policy outlines broad expectations regarding the professional image MDHS employees are required to portray and includes uniform requirements | For Review | Yes | Ensure gender neutral uniform options are provided to all staff members, without the need to specifically request it. | Yes | Expand scope of policy to reference the potential needs or considerations of diverse groups. Cultural sensitivity and safety needs to be considered when employing people who identify as Aboriginal or Torres Strait Islander in all aspects including uniform. When employing someone living with a disability, extra consideration of their specific uniform needs may be required. Allowances may need to be considered to help people of all sexualities, cultures, religions and genders feel comfortable at work. Feedback mechanisms for staff to feel heard if there is an aspect of the uniform which leads to feelings of discomfort.
Occupational Health and Safety Policy | Policy | A policy to outline MDHS' committment to creating a safe environment for everyone at MDHS – employees, patients and visitors | For Review | Yes | Update the policy to use inclusive terminology (remove reference to pronouns, or make them inclusive). | Yes | It was identified that policy would be more inclusive if it contained references and a committment to cultural safety, to assist with safety in the organisation. For example cultural safety is important for people who identify as Aboriginal or Torres Strait Islander.
Recommend reviewing the policy to include people living with a disability who may have diverse or additional needs to assist with maintaining health and safety of themselves and others.
Recruitment and Selection Policy | Policy | A policy which details how MDHS utilises a fair and accessible process to attract and retain high performing employees who meet MDHS’ organisational values, behaviours, attitudes and required skills sets. | For Review | Yes | Feedback from employees is gathered and documented about their experience of the recruitment process. | Yes | Intersectionality compounds gender discrimination, which can be present in recruitment and selection processes.
Continue with manager/leadership education to reduce risk of unconscious bias during recruitment and selection process.
Volunteers Policy | Policy | The policy defines the process for MDHS volunteer recruitment, roles, responsibilities and limitations and how volunteers’ rights are protected. | For Review | Yes | Feedback from volunteers is gathered to improve systems and processes. | Yes | There are known barriers to volunteering for First Nations Peoples, newly arrived migrants and people with disabilities.
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review | Yes | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. | Yes | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.

## 2.1 Strategies and measures
Strategies and measures
Table 2.1 - Strategies and measures progress
Required | Required | Required | Recommended | Recommended | Recommended | Recommended
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Indicators key
List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Relevant indicator(s) 1: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. | 1. 2. 3. 4. 5. 6. 7. | Gender composition of all levels of the workforce. Gender composition of governing bodies. Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender. Sexual harassment in the workplace Recruitment and promotion practices in the workplace. Availability and utilisation of terms, conditions and pratices relating to: - family violence leave - flexible working arrangements - working arrangements supporting employees with family or caring responsibilities Gendered segregation within the workplace
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7
Promote the Board Chair and CEO as champions for gender equality, and MDHS’s commitment as a gender equality organisation through a public statement, the MDHS website and internal and external communications. | Complete | - MDHS has launched the GEAP. - GEAP is publically available via the MDHS Website. - GEAP includes a statement from Board Chair and CEO | - Both the CEO and Board Chair have made public statements and the MDHS GEAP has been launched. | 2022 | CEO | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 2
Provide a culturally safe workplace guided by a Cultural Safety Framework developed in consultation with Aboriginal and Torres Strait Islander peoples. | Not started | - Have not started this piece of work. - A Diversity and Inclusion Lead will commence in February 2024 who will drive this piece of work. |  | 2023 | - Gender Equity Committee - Reconciliation Action Plan Committee. | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 2
Use gender neutral job advertisements, interview invitations, specific recruitment and selection criteria and structured interviews. | Complete | - New interview guides have been developed and implemented across MDHS. The guide covers the recruitment lifecycle, and helps ensure gender neutrality. | - New guides have been implemented successfully. | 2023 | People & Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 2
Strive for gender – balanced composition of Executive and Leadership Team. | Ongoing | - Gender balance across the Executive has been achieved. - When developing internal working groups, gender equity has been achieved where possible, given the significant gender skew within MDHS to those that describe themselves as 'females'. | - MDHS ensures gender balance when considering and appointing individuals to internal working committees where possible. - Composition across a 5 person Executive is as balanced as possible. | 2025 | CEO | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 2
Consider gender equality, diversity and inclusion costs in annual budget preparations and ensure the infrastructure is in place to support a more inclusive and flexible workplace. | Ongoing |  |  | 2023 | CEO, Executive, People & Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 2
Invest in leadership capabilities to drive cultural change at the middle management level. | Complete | All middle managers have undertaken extensive leadership development programs which has increased their leadership capability. Plans in place to now involve the next level of leadership in the program in 2024. | Feedback gained from participants in the course was very positive. | 2022 | CEO & Executive | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 2
Promote opportunities for female staff to be leaders and spokespeople, such as involvement on committees, boards and networks and award nominations. | Ongoing | - All MDHS employees are provided with the opportunity no nominate for internal working groups / committees. Senior Managers are provided with the opportunity to sit on regional committees, and area specialists are involved at state level. - Over 90 members of the MDHS team were nominated for awards at the MDHS Annual Awards Evening. | - The number of people nominating to participate in various has increased. - A majority of those nominated for MDHS Awards defined themselves as 'female' | 2022 | CEO & Executive | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 2
Enhance existing processes and resources to support flexible working arrangements, including exploring new and innovative ways to embed flexibility. | Complete | An increased focus on promoting flexible work plans has taken place via Induction sessions and all of staff member meetings. | The MDHS People Matters Survey for late 2023 indicates an increased number of MDHS employees are aware of flexible work plans, and an increased number of staff had accessed flexible work plans. An increased number of staff also indicated that they feel they would be provided with a flexible work plan if they requested one. | 2022 | People & Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 1
Redevelop recruitment material to ensure that gender and intersectionality information is gathered. | Ongoing | - New forms have been developed which are forwarded to successful candidates during their on boarding process. - An all of organisation survey was also undertaken so that existing staff could update their personal details. | - New forms are being distributed and completed by new employees. - Survey was made available to all employees, and was undertaken by a small number of our team. Will be undertaken again in 2024. | 2023 | People & Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 7
Ensure all employees have access to appropriate facilities, equipment and uniform based on their needs that do not make them feel vulnerable or disrespected. | Complete | - A thorough review of facilities across MDHS campuses was undertaken, and alterations were made where necessary. - As part of building the new hospital, a gender equity lens was taken. - Uniform policy has been reviewed and updated to incorporate more choice. | - Uni Sex toilets have been made available. - Uniform policy now incorporates additional choice, allowing individuals the opportunity to choose preferred items of clothing. | 2022 | Executive | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 7
Ensure the organisation provides additional training and access to resources on gender equality and increases awareness of intersectional factors so that teams can support inclusion and diversity. | Ongoing | - Intersectionality is explained and discussed as part of the Respect@MDHS program which is delivered at all MDHS Induction sessions - Diversity and Inclusions education to be added to the MDHS Education Training Schedule as a core item. - Newly appointed Diversity & Inclusion Lead to present at MDHS Induction. | - Intersectionality openly discussed and educated on a monthly basis at Induction. | 2023 | Organisational Development | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 7
Ensure all recruitment processes use a gender-balanced interview panel. When using recruitment agencies ensure they are adhering to the MDHS gender equality requirements and reporting on gender splits in the shortlisting and interviewing process. | Complete | - Internal policy and procedure has been updated to reflect interview panel requirements. - gender make up of recruitment panel to always include both males and females | Adopted by recruiting managers across MDHS without any concerns. | 2023 | People & Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Development of an Equal Opportunity Employment Policy. | Complete | - Policy has been developed, approved by Corporate Governance Committee and implemented across MDHS | - Recruiting managers have become increasingly aware of the listed protected attributes. | 2022 | People & Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Challenge traditional views of merit in recruitment and promotion assessment and evaluation. | Ongoing | - Have worked closely with recruiting managers to implement systems and processes that encourage a merit based approach. - All jobs are now advertised in accordance with EBA requirements, and are subject to interviews, no matter if applicants are internal. - Have moved away from recruiting the convenient applicant, to now recruiting the right applicant, which is actively assessed throughout the recruitment process. | - New hire success (the % of staff leaving before 6 months) is less than 1%, indicating that the right people are being recruited, based on skill base and values. | 2023 | CEO, People & Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Provide mentoring and support programs for women seeking promotion. | Not started | Will be focussed on by the Executive in 2024 |  | 2024 | Executive | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Provide the same benefits, training and promotional opportunities to women on flexible work and leave arrangements as other employees. | Complete | - All MDHS employees have the same level of access to Flexible working arrangements. | An increased number of flexible work plans have been implemented throughout 2023 as described in the People Matters Survey Results. | 2023 | People & Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Review remuneration policy with clear and transparent processes, including objective criteria for allocating benefits, with all remuneration linked to objective performance measures that consider gender. | Void/cancelled | - After further investigation, MDHS has little ability to influence its remuneration framework, as it does not negotiate its own enterprise agreements. This function is undertaken by the Victorian Hospital Industrial Association (VHIA) on behalf of all public sector hospitals. - VHIA do attempt to incorporate gender equity measures throughout the bargaining process, however MDHS have limited ability to influence negotiations. | - Not implemented as MDHS does not have the capability to influence state remuneration policy. | 2023 | CEO, People & Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 3
Develop and implement initiatives aimed at reducing existing gap in the Median annualised base salary (currently is 8.7% in favour of men) and Median total remuneration is (currently -3.2% which means 3.2% in favour of women). | Void/cancelled | - After further investigation, MDHS has little ability to influence its remuneration framework, as it does not negotiate its own enterprise agreements. This function is undertaken by the Victorian Hospital Industrial Association (VHIA) on behalf of all public sector hospitals. - VHIA do attempt to incorporate gender equity measures throughout the bargaining process, however MDHS have limited ability to influence negotiations. | - Not implemented as MDHS does not have the capability to influence state remuneration policy. | 2022 | CEO, Executive | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 3
Investigate partnerships with external agencies who can assist employee base with minimising the impact parental leave, unpaid leave has on income streams such as superannuation. | Void/cancelled | - After further investigation, MDHS has little ability to influence its remuneration framework, as it does not negotiate its own enterprise agreements. This function is undertaken by the Victorian Hospital Industrial Association (VHIA) on behalf of all public sector hospitals. - VHIA do attempt to incorporate gender equity measures throughout the bargaining process, however MDHS have limited ability to influence negotiations. | - Not implemented as MDHS does not have the capability to influence state remuneration policy. | 2024 | People & Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 3
- Ensure employees on flexible work arrangements have access to meaningful and quality work. This includes the same benefits, training and promotional opportunities as other employees. | Complete | - New systems and processes have been implemented to ensure those on flexible work arrangements have clear performance plans in place to assist them in working from home / flexibly. - Staff are provided with the ability to undertake training remotely and have the same benefits as those working onsite. - There is no impact on promotional opportunities, as clear work plans are in place to ensure the efficient management and monitoring of work performance. | - The number of employees seeking access to flexible workplace agreements has increased throughout 2023. | 2022 | CEO, People & Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
- Support carers to return to work after parental leave and take steps to minimise disruption to their career progress. | Complete | - Keeping in touch days are implemented to assist staff return from leaves of parental leave. - Superannuation on unpaid leave is paid to limit impact on those needing to extend period of maternity leave beyond the funded period. | - Keeping in touch days are regularly implemented for those returning to the workplace. - Leadership Team members are actively promoting 'Keeping in touch days". | 2022 | Executive, Leadership Team, People & Culture. | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
- Support managers to have the capability and confidence to effectively manage flexible work arrangements and build a culture where flexibility is fully embedded for their employees | Complete | - Ongoing manager education in place to ensure that they are willing and able to discuss flexible work plan applications with their teams without regular People and Culture intervention. | - There has been an increased number of flexible work plans implemented during 2022 and 2023. - Managers are not seeking out People & Culture support as frequently when requests are submitted for flexibility. | 2023 | Executive, People & Culture. | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
Provide flexible parental, carer and family violence leave regardless of gender. | Complete | - As per the EBA's MDHS implements, parental, carer and family violence leave is available to all staff regardless of gender. | - Parental, carer and family violence leave have been provided to a range of genders over past two years. | 2022 | CEO, Executive | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
Promote flexible working arrangement options highlighting different genders. | Complete | - Flexible working arrangements have been promoted to the entire staff team over the past two years. - There has been an increase the number of flexible work plan in place. | - The number of active flexible working arrangments has increased across MDHS over the past two years. | 2023 | People & Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
Review overtime and shift arrangements to make sure access is provided equally to male, female and gender diverse employees. | Not started | - Has not taken place and will be a priority for the newly appointed Diversity and Inclusion Lead - in consultaion with Managers. |  | 2023 | People & Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
Ensure leadership and professional development opportunities are provided through flexible means allowing an equal number of opportunities for participation. | Complete | - Leadership courses have been offered via a range of mediums, including online and in person. | A range of courses have been undertaken by staff at all levels of MDHS. Mediums include conference presentations, completing development programs and undertaken role based education. | 2023 | Executive, Oranisation Development | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
Develop a communication plan that supports reinforcement of messaging from CEO and Executive Team on zero tolerance approach to harassment, discrimination, unfair treatment and sexism. | Not started | - Has been unintentionally missed in 2023, and will be actioned in 2024 by the newly appointed Diversity & Inclusion Lead. | - To be determined. |  | CEO, Executive | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 4
Development and implementation a workplace respect program (Respect@MDHS) which informs staff of their workplace rights under the OHS Act (Vic), clearly defines acceptable behaviour, and the structures in place at MDHS to assist address reported instances of unacceptable behaviour. | Ongoing | - The Respect@MDHS program has been in place since 2022, and is delivered by a number of trained presenters. All staff entering the organisation have completed the program as part of their induction program. Sessions are also planned to run across MDHS on a monthly basis in upcoming months. | - Participant feedback has been excellent, and indicates that our team’s understanding of acceptable / unacceptable workplace behaviours has increased. Participants have also indicated that they are now more confident in reporting inappropriate behaviour if they see/receive it. | 2022 | People & Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 4
Identify and educate “Employee Relations Contact Officers”. Multiple Contact Officers to be installed at each MDHS Campus. | Complete | - New Contact Officers were engaged and trained in 2022, and they reside at all 3 MDHS Campuses. | - Contact Officers are actively supported by the People & Culture Manager, and are being engaged by MDHS Team members from time-to-time. | 2022 | People & Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 4
Develop and implement a program of activities and events to engage and support informal learning and build awareness of gender equality and intersectional factors, including International Women’s Day, Wear it Purple Day, and significant cultural events including National Reconciliation week and NAIDOC week. | Complete | - In 2023 MDHS celebrated Wear it Purple Day and NAIDOC week. | - Wear it Purple Day's success is demonstrated by the participation in specific activities across our 3 campuses. Participation levels increased on previous years. - NAIDOC week activities at the NEST were community focussed and generated significant participation in activities by the community, from all ages. Led by the MDHS Aboriginal Liaison Officers. | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 4
Develop and distribute an internal campaign and tools that clearly articulate what sexism and discrimination looks like and how to call out and prevent it. | Not started | - Has been unintentionally missed in 2023, and will be actioned in 2024 by the newly appointed Diversity & Inclusion Lead. | - To be determined. | 2023 | People & Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 4
Select one
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 1: Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | 2022 | People and Culture Corporate Support | bar: Relevant indicator(s) 1 to Relevant indicator(s) 3; Relevant indicator(s) 5 to Relevant indicator(s) 7

## 2.2 Resourcing your GEAP
Resourcing your GEAP
Table 2.2 - Allocation of resources to implement the strategies and measures in your GEAP
Recommended
You might consider some or all of the following, in addition to any other aspects you consider relevant: • Who implements the strategies and measures in your GEAP? What role do they perform at what level in your defined entity? • How many staff members/FTE are allocated to implementing the strategies and measures? • Was enough resourcing allocated to successfully implement your strategies and measures? If not, how will this be addressed?
Your Comments
Initially, the implementation of the GEAP was added to an existing role. However, given the significant workload generated by relevant legislation, it was decided to recruit to a Diversity and Inclusion Lead, who is responsible for managing the Diversity and Inclusion portfolio - and ensuring compliance with relevant legislation. MDHS has just recruited to a Diversity and Inclusion Lead at 0.8 EFT. MDHS will monitor the workload of the Diversity and Inclusion Lead and determine if the resource allocation is enough to ensure compliance and cultural change.

## 3 Indicators
Workplace Gender Equality Indicators
Table 3 - Workplace gender equality indicators progress
Required | Required | Required | Recommended | [6 empty] | Recommended | Factors key:
|  |  | Factors | [7 empty] | a. b. c. d. e. f. g. | The size of the defined entity, including the defined entity's number of employees. The nature and circumstances of the defined entity, including any barriers to making progress. Requirements that apply to the defined entity under any other Act, including an Act of the Commonwealth. The defined entity's resources. The defined entity's operational priorities and competing operational obligations. The practicability and cost to the defined entity of making progress. Genuine attempts made by the defined entity to make progress.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
Gender composition of all levels of the workforce | Yes | As per the MDHS GEAP, a specific focus has been placed upon the promotion and implementation of flexible working agreements. During the reporting period, 37 members of our team took up the opportunity to work flexibly. As described in the 2023 People Matters Survey, 69% of our team indicated that they felt they would be given access to a flexible workplace agreement if requested, which is an increase of 14% from the previous years survey. Additionally, 63% of our team indicated that their manager supported flexible working arrangements, which is a 13% increase from the 2022 survey. | No | No | No | No | No | No | No
Gender composition of governing bodies | Yes | At the conclusion of June 2023, the MDHS Board considered of 3 males Directors, 4 female directors and 1 female Chairperson. When data was collated for the previous workplace gender audit, the composition of the MDHS Board was 5 male Directors, 3 female Directors and 1 Male Board Chair | No | No | No | No | No | No | No
Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender | No | All MDHS employees (apart from the CEO) are employed under relevant enterprise agreements. Given enterprise agreements are negotiated by the Victorian Hospitals Industry Association - on behalf of the Victorian Government, there is little ability for MDHS to influence the remuneration levels agreed to throughout the negotiating process. Therefore, inequity exists across the enterprise agreements implemented at MDHS, as roles with similar levels of accountability are not remunerated at the same level. | No | Yes | No | No | No | No | No | As described, MDHS does not have the ability to infuence the Deparment of Health's remuneration policy - and EBA's are negotiated by a third party (VHIA), who do not take direction by hospitals such as MDHS.
Sexual harassment in the workplace | Yes | MDHS has implemented face to face training titled "Respect@MDHS" during the reporting period and has had 100% of new starters complete the training. The Respect@MDHS program highlights inappropriate behaviour, and informs employees of their protections, and how they may choose to address any matters of bullying and harassment. During the reporting period 2 instances of sexual harassment were made, which is 2 more than in the initial workforce report. Contact Officers across all MDHS sites have been identified, trained and installed successfully. As outlined in the 2021 Workforce Reporting Submission, MDHS was not able to capture this data previously, so no comparison is able to be made. Our systems now allow this data to be captured. | No | No | No | No | No | No | No
Recruitment and promotion practices in the workplace | Yes | As described in the MDHS GEAP, an Equal Employment Opportunity Policy has been developed and implemented. Via organisation wide education initiatives, recruiting managers are fully aware of their requirements and are adhered to at all times. A GIA has been undertaken on Recruitment and Selection Policy - which resulted in frameworks being included which request gender balance on shortlisting and interview panels. A remuneration/promotions committee has also been developed and implemented, which is charged with equitably reviewing any application for a remuneration increase/promotion. | No | No | No | No | No | No | No
Availability and utilisation of terms, conditions and practices relating to: - family violence leave; and - flexible working arrangements; and - working arrangements supporting employees with family or caring responsibilities | Yes | Significant education has been implemented regarding the availability of Family Violence leave, and the ability to access flexible workplace arrangements. During the reporting period, 12 members of our team accessed family violence leave, whilst 37 members of our team took the opportunity to access flexible working arrangements. . In 2021, MDHS did not capture this information, and as such, enhancements have been made to the Human Resource Information System to ensure the data is being captured accurately. | No | No | No | No | No | No | No
Gendered segregation within the workplace | Yes | MDHS has implemented all of the initiatives outlined in its GEAP in this space. As such all 100% of recruitment material has been reviewed via a GIA and intersectionality information is being gathered of all new starters. Additionally, every MDHS staff member was provided with the opportunity to update their staff profile via an online survey, of which a small percentage of staff undertook. This survey will be implemented again in mid-2024. The MDHS uniform policy has also been reviewed, and updated to ensure more choice was available to staff members. Additional items of clothing were also added. The MDHS education program has also been fully reviewed, and modules relating to Gender Equity have been developed, and will be facilitated by the Gender Equity and Diversity Lead. It is important to note, that this role had not been recruited to at the end of the reporting period. | No | No | No | No | No | No | No
Example(s)
Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  | a | b | c | d | e | f | g
Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## Examples (hidden)
1 Gender impact assessments
| Title | Subject | Description | Status |  |  | Confirm if actions taken |  |  |  | Describe actions taken |  | Confirm intersectionality considered |  | Explain intersectional lens applied
| What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. |  |  | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. |  |  |  | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. |  | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. |  | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
| Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review |  |  | Yes |  |  |  | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. |  | Yes |  | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.
2.1 Strategies and measures
| Strategies and measures | Status | Status description | Evaluation of success | [6 empty] | Timeline | Responsible | Relevant indicator(s)
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | [6 empty] | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Relevant indicator(s) 1: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator.
| Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | [6 empty] | 2022 | People and Culture Corporate Support | bar: Relevant indicator(s) 1 to Relevant indicator(s) 3; Relevant indicator(s) 5 to Relevant indicator(s) 7
3 Workplace Gender Equality Indicators
| Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  |  | a | b | c | d | e | f | g
| This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
| Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
| Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## (Hidden) REF (hidden)
Policy | New | Yes | Select one | Yes
Program | For Review | No | Complete | No action taken
Service |  |  | In progress
Ongoing
Not started
Void/cancelled